# Veldra Insights — Monthly Launch Status

February 2026 edition  ·  Prepared by Ana Delgado, Product Marketing  ·  Issued March 1, 2026

Distribution: Diane Whitfield; launch core team

## Executive summary

Veldra Insights closed February on track for general availability on March 15, with the beta cycle complete and paid media expanded following the mid-month budget revision. Final beta results landed just under target — NPS 47 against a goal of 50, with the waitlist at 4,820 — strong enough to proceed while we tighten onboarding. Two items remain on the critical path into March: legal sign-off on the pricing-page claims, and creative capacity, which is running lean through month-end due to the rebrand reallocation.

## Key metrics

| Metric | Current | Target | Status |
| --- | --- | --- | --- |
| Waitlist signups | 4,820 (Feb 23) | 5,000 | 🟡 On track |
| Beta NPS | 47 (n=214) | 50 | 🟡 Below target |
| Campaign budget | $275,000 | — | 🟢 Approved |
| Launch-sourced pipeline | $255,000 (Feb 28) | — | 🟢 Building |

## Pipeline trajectory

Launch-attributed pipeline has built steadily through the quarter as opportunities progress toward close.

## Workstream status

| Workstream | Owner | Status | Note |
| --- | --- | --- | --- |
| Pricing page & legal review | Priya Raman / Tomas Keller | 🟡 In progress | Legal review of claims pending; required before publish |
| Press & analyst briefing | Ana Delgado | 🟢 Scheduled | March 8, 9:00am PT |
| Paid media | Ana Delgado | 🟢 On track | Expanded after Feb 12 budget increase |
| Localization (DACH) | — | ⚪ Deferred | Moved to wave 2 (targeted May) per January scope decision |
| Press kit assets | Lena Park | 🟡 At risk | Timeline tight given creative capacity |
| Creative capacity | Marcus Chen | 🟡 At risk | Operating at 3 through March (Marcus 50% on rebrand) |

## Risks & watch-items

Legal review of pricing-page claims is not yet started as of this report; required before the page can publish.

Creative capacity is reduced through March; the press-kit timeline is at risk.

The creative agency contract renewal is on track for April.

## Outlook — next 30 days

General availability (GA): March 15, 2026, with the announcement at 9:00am PT.

Press & analyst briefing: March 8, 2026.

Waitlist nurture email sequence begins March 10.

Final legal sign-off on pricing-page claims expected ahead of publish.